## Budget vs actual cost
Row Labels | Sum of Budget (INR) | Sum of Actual Cost (INR)
Bangalore | 273000000 | 276800000
Chennai | 203000000 | 208000000
Delhi | 111000000 | 114400000
Hyderabad | 269000000 | 277900000
Kolkata | 270000000 | 271500000
Mumbai | 165000000 | 166800000
Pune | 121000000 | 124400000
Grand Total | 1412000000 | 1439800000
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.

## Location vs Incidents
Row Labels | Sum of Site Incidents
Hyderabad | 34
Chennai | 25
Kolkata | 20
Bangalore | 16
Mumbai | 13
Pune | 10
Delhi | 9
Grand Total | 127
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.

## Delayed project
Row Labels | Sum of Planned Duration (days) | Sum of Actual Duration (days)
Project_15 | 529 | 612
Project_26 | 524 | 577
Project_35 | 523 | 575
Project_44 | 529 | 530
Project_43 | 478 | 518
Project_7 | 518 | 517
Project_2 | 482 | 506
Project_34 | 469 | 505
Project_17 | 491 | 486
Project_6 | 462 | 469
Grand Total | 5005 | 5295
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.

## Top 10 expensive project
Row Labels | Sum of Actual Cost (INR)
Project_30 | 51000000
Project_46 | 48300000
Project_21 | 48000000
Project_3 | 47200000
Project_28 | 46700000
Project_48 | 46600000
Project_38 | 46300000
Project_44 | 46300000
Project_6 | 45900000
Project_26 | 45300000
Grand Total | 471600000
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.

## Dashboard
🏗️ Construction Project Dashboard
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.

## construction_project_data
Project Name | Location | Start Date | Planned End Date | Actual End Date | Planned Duration (days) | Actual Duration (days) | Budget (INR) | Actual Cost (INR) | Materials Used | Average Daily Labor | Site Incidents
Project_1 | Pune | 2023-02-27 | 2023-09-07 | 2023-11-10 | 192 | 256 | 22000000 | 21700000 | Steel, Tiles, Cement | 116 | 5
Project_2 | Chennai | 2023-02-14 | 2024-06-10 | 2024-07-04 | 482 | 506 | 7000000 | 6000000 | Cement, Steel, Wood | 94 | 4
Project_3 | Mumbai | 2023-10-15 | 2024-07-22 | 2024-09-21 | 281 | 342 | 46000000 | 47200000 | Glass, Concrete, Steel | 87 | 4
Project_4 | Bangalore | 2023-01-04 | 2023-09-22 | 2023-11-20 | 261 | 320 | 32000000 | 32000000 | Bricks, Steel, Wood | 73 | 0
Project_5 | Mumbai | 2023-07-14 | 2024-02-28 | 2024-03-14 | 229 | 244 | 27000000 | 27900000 | Bricks, Cement, Concrete | 98 | 0
Project_6 | Hyderabad | 2023-02-10 | 2024-05-17 | 2024-05-24 | 462 | 469 | 45000000 | 45900000 | Tiles, Bricks, Glass | 54 | 5
Project_7 | Mumbai | 2023-01-24 | 2024-06-25 | 2024-06-24 | 518 | 517 | 23000000 | 22200000 | Tiles, Steel, Cement | 78 | 2
Project_8 | Hyderabad | 2023-07-06 | 2024-03-25 | 2024-04-11 | 263 | 280 | 27000000 | 26600000 | Wood, Bricks, Cement | 107 | 5
Project_9 | Delhi | 2023-10-01 | 2024-08-01 | 2024-07-22 | 305 | 295 | 34000000 | 34200000 | Bricks, Wood, Glass | 58 | 5
Project_10 | Bangalore | 2023-01-29 | 2023-11-22 | 2024-02-05 | 297 | 372 | 7000000 | 8500000 | Bricks, Concrete, Tiles | 38 | 1
Project_11 | Chennai | 2023-06-11 | 2024-03-25 | 2024-05-17 | 288 | 341 | 36000000 | 36200000 | Wood, Concrete, Steel | 63 | 1
Project_12 | Delhi | 2023-10-15 | 2025-01-12 | 2025-01-15 | 455 | 458 | 42000000 | 42300000 | Glass, Concrete, Bricks | 58 | 1
Project_13 | Chennai | 2023-09-10 | 2024-04-23 | 2024-06-28 | 226 | 292 | 8000000 | 9700000 | Cement, Steel, Wood | 117 | 3
Project_14 | Chennai | 2023-02-02 | 2024-02-14 | 2024-03-03 | 377 | 395 | 43000000 | 43400000 | Glass, Bricks, Tiles | 31 | 5
Project_15 | Pune | 2023-02-28 | 2024-08-10 | 2024-11-01 | 529 | 612 | 39000000 | 40400000 | Bricks, Wood, Tiles | 44 | 2
Project_16 | Hyderabad | 2023-03-22 | 2024-05-07 | 2024-04-07 | 412 | 382 | 21000000 | 21600000 | Tiles, Steel, Glass | 43 | 5
Project_17 | Bangalore | 2023-09-17 | 2025-01-20 | 2025-01-15 | 491 | 486 | 14000000 | 14100000 | Tiles, Steel, Glass | 97 | 0
Project_18 | Chennai | 2023-06-15 | 2024-08-18 | 2024-07-21 | 430 | 402 | 12000000 | 13900000 | Bricks, Tiles, Steel | 37 | 1
Project_19 | Chennai | 2023-02-10 | 2023-09-21 | 2023-11-23 | 223 | 286 | 36000000 | 37600000 | Cement, Glass, Steel | 46 | 5
Project_20 | Hyderabad | 2023-10-09 | 2024-06-29 | 2024-07-02 | 264 | 267 | 38000000 | 39700000 | Glass, Concrete, Steel | 99 | 5
Project_21 | Pune | 2023-04-13 | 2024-03-17 | 2024-04-07 | 339 | 360 | 47000000 | 48000000 | Bricks, Concrete, Glass | 87 | 0
Project_22 | Delhi | 2023-04-26 | 2023-11-24 | 2023-12-07 | 212 | 225 | 6000000 | 6800000 | Glass, Steel, Tiles | 58 | 0
Project_23 | Mumbai | 2023-01-31 | 2023-11-24 | 2023-11-02 | 297 | 275 | 7000000 | 8700000 | Bricks, Cement, Glass | 60 | 2
Project_24 | Pune | 2023-09-06 | 2024-06-21 | 2024-07-30 | 289 | 328 | 13000000 | 14300000 | Glass, Tiles, Concrete | 61 | 3
Project_25 | Kolkata | 2023-07-28 | 2024-04-30 | 2024-04-12 | 277 | 259 | 11000000 | 12100000 | Concrete, Bricks, Tiles | 82 | 3
Project_26 | Kolkata | 2023-01-28 | 2024-07-05 | 2024-08-27 | 524 | 577 | 46000000 | 45300000 | Cement, Concrete, Bricks | 43 | 1
Project_27 | Delhi | 2023-04-08 | 2024-07-05 | 2024-08-01 | 454 | 481 | 13000000 | 13300000 | Steel, Bricks, Concrete | 61 | 0
Project_28 | Hyderabad | 2023-10-09 | 2024-05-26 | 2024-05-02 | 230 | 206 | 46000000 | 46700000 | Tiles, Cement, Wood | 60 | 1
Project_29 | Hyderabad | 2023-09-06 | 2024-11-05 | 2024-11-02 | 426 | 423 | 30000000 | 31800000 | Cement, Steel, Concrete | 30 | 3
Project_30 | Bangalore | 2023-08-21 | 2024-07-12 | 2024-08-05 | 326 | 350 | 49000000 | 51000000 | Wood, Glass, Concrete | 49 | 1
Project_31 | Bangalore | 2023-04-22 | 2023-11-17 | 2023-12-31 | 209 | 253 | 39000000 | 38100000 | Wood, Bricks, Cement | 36 | 4
Project_32 | Hyderabad | 2023-09-15 | 2024-12-09 | 2024-11-29 | 451 | 441 | 8000000 | 10000000 | Glass, Cement, Steel | 38 | 4
Project_33 | Mumbai | 2023-05-01 | 2024-05-21 | 2024-05-06 | 386 | 371 | 41000000 | 40700000 | Glass, Tiles, Cement | 109 | 0
Project_34 | Hyderabad | 2023-10-26 | 2025-02-06 | 2025-03-14 | 469 | 505 | 25000000 | 26900000 | Bricks, Steel, Tiles | 60 | 2
Project_35 | Hyderabad | 2023-03-09 | 2024-08-13 | 2024-10-04 | 523 | 575 | 24000000 | 24400000 | Bricks, Cement, Wood | 88 | 4
Project_36 | Chennai | 2023-02-21 | 2023-09-26 | 2023-11-03 | 217 | 255 | 18000000 | 18600000 | Bricks, Steel, Tiles | 38 | 1
Project_37 | Bangalore | 2023-05-26 | 2024-02-10 | 2024-03-07 | 260 | 286 | 39000000 | 40200000 | Bricks, Glass, Wood | 31 | 5
Project_38 | Kolkata | 2023-10-11 | 2024-09-08 | 2024-12-06 | 333 | 422 | 47000000 | 46300000 | Steel, Bricks, Cement | 43 | 5
Project_39 | Chennai | 2023-03-21 | 2024-02-03 | 2024-02-09 | 319 | 325 | 43000000 | 42600000 | Wood, Bricks, Steel | 117 | 5
Project_40 | Kolkata | 2023-05-16 | 2024-07-27 | 2024-08-28 | 438 | 470 | 21000000 | 22800000 | Tiles, Cement, Wood | 111 | 3
Project_41 | Kolkata | 2023-05-22 | 2023-12-10 | 2023-11-10 | 202 | 172 | 26000000 | 27400000 | Steel, Wood, Bricks | 50 | 5
Project_42 | Hyderabad | 2023-10-10 | 2024-11-11 | 2024-12-22 | 398 | 439 | 5000000 | 4300000 | Cement, Wood, Steel | 99 | 0
Project_43 | Kolkata | 2023-07-09 | 2024-10-29 | 2024-12-08 | 478 | 518 | 14000000 | 14300000 | Steel, Cement, Bricks | 76 | 0
Project_44 | Bangalore | 2023-04-18 | 2024-09-28 | 2024-09-29 | 529 | 530 | 47000000 | 46300000 | Bricks, Glass, Concrete | 109 | 5
Project_45 | Delhi | 2023-05-02 | 2024-01-20 | 2024-04-01 | 263 | 335 | 16000000 | 17800000 | Concrete, Cement, Steel | 72 | 3
Project_46 | Kolkata | 2023-05-08 | 2024-03-19 | 2024-03-09 | 316 | 306 | 49000000 | 48300000 | Concrete, Cement, Tiles | 58 | 1
Project_47 | Kolkata | 2023-08-24 | 2024-08-17 | 2024-08-26 | 359 | 368 | 19000000 | 18700000 | Cement, Wood, Steel | 81 | 2
Project_48 | Bangalore | 2023-02-05 | 2023-12-24 | 2024-01-07 | 322 | 336 | 46000000 | 46600000 | Concrete, Wood, Glass | 72 | 0
Project_49 | Mumbai | 2023-05-14 | 2024-02-09 | 2024-03-24 | 271 | 315 | 21000000 | 20100000 | Cement, Glass, Concrete | 74 | 5
Project_50 | Kolkata | 2023-06-10 | 2024-07-17 | 2024-09-02 | 403 | 450 | 37000000 | 36300000 | Concrete, Glass, Steel | 62 | 0